## Sheet1
Priority | UseCase ID | User Story | Story Points
1 | US-01 | As an user I want a web interface in order to control SHAS Testbed system | 10
2 | US-02 | As an User I want to be able to enters a username a password to log into the SHAS Testbed system | 5
3 | US-03 | As an User I want the SHAS system to monitor security sensors so that the system reports any unauthorized access | 10
4 | US-04 | As an User I want the SHAS system to contact the police if security sensors a tripped for my safety | 10
5 | US-05 | As an User I want to be able to set sprinkler settings from the SHAS system to reduce water usage | 2
6 | US-09 | As an User I want to be able to control HVAC settings to control house temperature through the SHAS system | 5
7 | US-10 | As an User I want the SHAS system to monitor the fire, CO, gas alarms so that the system reports any emergencies | 5
8 | US-06 | As an User I want to view water usage reports to be able to monitor water usage | 5
9 | US-07 | As an User I want to view Electric usage report to be able to monitor electricity usage | 5
10 | US-08 | As an User I want the SHAS system to control HVAC settings to reduce energy consumption | 10
11 | US-11 | As an User when fire, CO, gas alarms are activated I want the SHAS system to contact the fire department for my safety | 10
12 | US-12 | As an User I want to get notified when windows or doors are left open to reduce energy consumption | 2
13 | US-13 | As an User I want a smart phone application to control SHAS system | 10
14 | US-14 | As an User I want to be able to check Smart power outlets in use and sets their specific settings to monitor electricity usage | 10
15 | US-15 | As an User I want to be able to turn on sunlight sensors that control room lights in order to save energy | 5
16 | US-16 | As an User I want to be able to check the state of the lights of the SHAS and turns them on/off in order to save energy | 5
Sprint 1
| UseCase ID | User Story | To Do | In Progress | Done
| US-01 | As an user I want a web interface in order to control SHAS Testbed system
•Smart House web UI
•Testbed web UI
| US-02 | As an User I want to be able to enters a username a password to log into the SHAS Testbed system
•Login web page(Single User)
| US-03 | As an User I want the SHAS system to monitor security sensors so that the system reports any unauthorized access
•Code Testbed Simulation
•Code Smart House
•Code Alarm system
•Code Notify Users
| US-04 | As an User I want the SHAS system to contact the police if security sensors a tripped for my safety
•Alarm web UI
•Testbed Event Handler
•Code False Alarm Event
•Code Notify Police
| US-05 | As an User I want to be able to set sprinkler settings from the SHAS system to reduce water usage
•Sprinkler web UI
•Code Sprinkler System
•Code Sprinkler Zones
•Code Sprinkler
Sprint 2
| UseCase ID | User Story | To Do | In Progress | Done
| US-01 | As an user I want a web interface in order to control SHAS Testbed system
Smart House web UI
Testbed web UI
| US-02 | As an User I want to be able to enters a username a password to log into the SHAS Testbed system
Log Out
| US-03 | As an User I want the SHAS system to monitor security sensors so that the system reports any unauthorized access
Code Testbed Simulation
Code Smart House
| US-04 | As an User I want the SHAS system to contact the police if security sensors a tripped for my safety
Alarm web UI
Alarm On/Off specific time
Testbed Event Handler
| US-05 | As an User I want to be able to set sprinkler settings from the SHAS system to reduce water usage
Sprinkler web UI
| US-09 | As an User I want to be able to control HVAC settings to control house temperature through the SHAS system
Thermostat web UI
CodeThermostat
| US-10 | As an User I want the SHAS system to monitor the fire, CO, gas alarms so that the system reports any emergencies
Code Fire Sensors
Fire Sensors web UI