## Sheet1
Priority | UseCase ID | User Story | Story Points | Sprint 1 Left Over | Sprint 2 Left Over
1 | US-01 | As an user I want a web interface in order to control SHAS Testbed system | 10 | 10 | 5
2 | US-02 | As an User I want to be able to enters a username a password to log into the SHAS Testbed system | 5 | 0 | 0
| US-02.1 | Log Out of web interface (Added After Sprint 1) | 2 |  | 0
| US-2.2 | Lock User Account after 3 unsucessfull logins | 3
5 | US-03 | As an User I want the SHAS system to monitor security sensors so that the system reports any unauthorized access | 10 | 3 | 0
| US-03.1 | Alarm On/Off at specific Times(Added After Sprint 1) | 2 |  | 0
7 | US-04 | As an User I want the SHAS system to contact the police if security sensors a tripped for my safety | 10 | 4 | 2
8 | US-05 | As an User I want to be able to set sprinkler settings from the SHAS system to reduce water usage | 2 | 1 | 1
| US-05.1 | I want to set sprinkler settings in a monthly basis | 3
10 | US-09 | As an User I want to be able to control HVAC settings to control house temperature through the SHAS system | 5 |  | 4
11 | US-10 | As an User I want the SHAS system to monitor the fire, CO, gas alarms so that the system reports any emergencies | 5 |  | 4
12 | US-11 | As an User when fire, CO, gas alarms are activated I want the SHAS system to contact the fire department for my safety | 5 |  | 5
13 | US-06 | As an User I want to view water usage reports to be able to monitor water usage | 5
14 | US-07 | As an User I want to view Electric usage report to be able to monitor electricity usage | 5
15 | US-08 | As an User I want the SHAS system to control HVAC settings to reduce energy consumption | 10
16 | US-12 | As an User I want to get notified when windows or doors are left open to reduce energy consumption | 2
17 | US-13 | As an User I want a smart phone application to control SHAS system | 10
18 | US-14 | As an User I want to be able to check Smart power outlets in use and sets their specific settings to monitor electricity usage | 10
19 | US-15 | As an User I want to be able to turn on sunlight sensors that control room lights in order to save energy | 5
20 | US-16 | As an User I want to be able to check the state of the lights of the SHAS and turns them on/off in order to save energy | 5
Sprint 1
| UseCase ID | User Story | To Do | In Progress | Done | Done Points
| US-01 | As an user I want a web interface in order to control SHAS Testbed system |  |  |  | 0
•Smart House web UI
•Testbed web UI
| US-02 | As an User I want to be able to enters a username a password to log into the SHAS Testbed system |  |  |  | 5
•Login web page(Single User)
| US-03 | As an User I want the SHAS system to monitor security sensors so that the system reports any unauthorized access |  |  |  | 7
•Code Testbed Simulation
•Code Smart House
•Code Alarm system
•Code Notify Users
| US-04 | As an User I want the SHAS system to contact the police if security sensors a tripped for my safety |  |  |  | 6
•Alarm web UI
•Testbed Event Handler
•Code False Alarm Event
•Code Notify Police
| US-05 | As an User I want to be able to set sprinkler settings from the SHAS system to reduce water usage |  |  |  | 1
•Sprinkler web UI
•Code Sprinkler System
•Code Sprinkler Zones
•Code Sprinkler
Sprint 2
| UseCase ID | User Story | To Do | In Progress | Done | Done Points
| US-01 | As an user I want a web interface in order to control SHAS Testbed system |  |  |  | 5
Smart House web UI
Testbed web UI
| US-02.1 | Log out of web Interface |  |  |  | 2
Log Out
| US-03 | As an User I want the SHAS system to monitor security sensors so that the system reports any unauthorized access |  |  |  | 3
Code Testbed Simulation
Code Smart House
| US-04 | As an User I want the SHAS system to contact the police if security sensors a tripped for my safety |  |  |  | 2
Alarm web UI
Testbed Event Handler
| US-04.1 | Turn Alarm on/off |  |  |  | 2
Alarm On/Off specific time
| US-05 | As an User I want to be able to set sprinkler settings from the SHAS system to reduce water usage |  |  |  | 0
Sprinkler web UI
| US-09 | As an User I want to be able to control HVAC settings to control house temperature through the SHAS system |  |  |  | 1
Thermostat web UI
CodeThermostat
| US-10 | As an User I want the SHAS system to monitor the fire, CO, gas alarms so that the system reports any emergencies |  |  |  | 1
Code Fire Sensors
Fire Sensors web UI
| US-11 | As an User when fire, CO, gas alarms are activated I want the SHAS system to contact the fire department for my safety |  |  |  | 0
Code Contact Fire Deparment
Code Contact Homeowners
Sprint 3
| UseCase ID | User Story | To Do | In Progress | Done | Done Points
| US-01 | As an user I want a web interface in order to control SHAS Testbed system
Smart House web UI
Testbed web UI
| US-02.2 | As an user if someone tries to log in to my account more than 3 times lock my account
Lock Account
Send Password Recovery Email
| US-05.1 | US-05.1 As an user I want to be able to set sprinkler settings in a monthly basis
Spinkler web UI changes
Sprinkler automation settings in a monthly schedule
| US-09 | As an User I want to be able to control HVAC settings to control house temperature through the SHAS system
Thermostat web UI
CodeThermostat
| US-10 | As an User I want the SHAS system to monitor the fire, CO, gas alarms so that the system reports any emergencies
Code Fire Sensors
Fire Sensors web UI
| US-11 | As an User when fire, CO, gas alarms are activated I want the SHAS system to contact the fire department for my safety
Code Contact Fire Deparment
Code Contact Homeowners